## Vitals
Project Vitals
End Customer | CRIS (Centre for Railway Information Systems)
Project Name | Procurement of Data Layer Solution for Next generation Passenger Reservation System of Indian Railways
Bid Due Date | 15th July 2025 (Online on IREPS portal)
Estimated project cost | INR 20 Cr for 2 sites (Delhi DC and Secunderabed DR)
Components | Software Supply and Services (no hardware)
Duration | SITC (14 weeks) + 3 years O&M + 2 years O&M (optional)
EMD | 20 Lacs
PBG | 4% of TCV for 3 years 3 months (Approx. INR 1.8 Cr.)
Penalty | Capped to 10% of TCV
Payment | Annual advance for Subscriptions and Quarterly deferred for Support
Targus Scope | Resident Engineers onsite (Approx. 10% of bid) for L1 support and vendor coordination on 24x7x365 basis at both DC and DR.
Bid Evaluation Process | Technical + Commercial + RA
Implementation ownership | HPE (Overall Solution) and respective product OEMs
OEM background | Incumbent OEMs already working with CRIS.
Partially Controlled Bid | HPE orchestrated the vid along with other OEMs.
Competitive Scenario | Hitachi, Tata Advans, Orbit Techsol and others
Competitive Scenario | Hitachi, Tata Advans, Orbit Techsol and others
Risks | • If other OEMs and partners come and bid. • Price sensitive scenario due to RA. • More competition compared to last time as PQs relaxed. • Less control or indepth knowledge of solution.
Win Strategy | HPE in control of Bid and OEMs and assured preferential pricing.

## Del & Pay Summ
Delivery & Payment Milestones
Sl. | Milestone | Timeline | Payment
1 | Software Delivery | 4 weeks from PO
2 | Installation & Configuration | 4 weeks (8 weeks from PO)
3 | FAT | 2 weeks (10 weeks from PO)
4 | Go Live | 4 weeks (14 weeks from PO)
5 | System Commissioning at Primary and DR site | On Go Live for 1st yr and annually for 2nd and 3rd yr | Yearly in Advance for Yr 1 Subscription cost + one Time Installation cost
6 | Training Completion |  | Training Cost
7 | Comprehensive support |  | Quarterly in arrears
8 | OEM Man days |  | Healf yearly in arrears on basis of comsumption

## SOR
Schedule of Requirements (SOR)
Sl. | Item Description | Technical Spec no. | UoM | Qty. | Line Item Wise SOW Defined | Product Offered | Remarks | PL No. | Milestone | Payment
A1 - Data layer for Primary DC -Mandatory
1 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Annual Subscription Cost for first year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 101 | M1 - 1 | Annual Advance
2 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Annual Subscription Cost for second year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 102 | M1 - 2 | Annual Advance
3 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Annual Subscription Cost for third year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 103 | M1 - 3 | Annual Advance
4 | Transactional Data Store -with supporting components and underlying Operating System for Staging environment -Annual Subscription Cost for first year - for Primary DC Note:-If the bidder does not required Subscription for Staging for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 104 | M1 - 1 | Annual Advance
5 | Transactional Data Store -with supporting components and underlying Operating System for Staging environment -Annual Subscription Cost for second year - for Primary DC Note:-If the bidder does not required Subscription for Staging for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 105 | M1 - 2 | Annual Advance
6 | Transactional Data Store -with supporting components and underlying Operating System for Staging environment -Annual Subscription Cost for third year - for Primary DC Note:-If the bidder does not required Subscriptionfor Staging for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 106 | M1 - 3 | Annual Advance
7 | Transactional Data Store -with supporting components for T & D environment -Annual Subscription Cost for first year - for Primary DC Note:-If the bidder does not required Subscriptionfor T&D for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 107 | M1 - 1 | Annual Advance
8 | Transactional Data Store -with supporting components for T & D environment -Annual Subscription Cost for second year - for Primary DC Note:-If the bidder does not required Subscription for T&D for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 108 | M1 - 2 | Annual Advance
9 | Transactional Data Store -with supporting components for T & D environment -Annual Subscription Cost for third year - for Primary DC Note:-If the bidder does not required Subscription for T&D for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 109 | M1 - 3 | Annual Advance
10 | RDBMS - with supporting components - Annual Subscription Cost for first year - for Primary DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 110 | M1 - 1 | Annual Advance
11 | RDBMS - with supporting components - Annual Subscription Cost for second year - for Primary DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 111 | M1 - 2 | Annual Advance
12 | RDBMS - with supporting components - Annual Subscription Cost for third year - for Primary DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 112 | M1 - 3 | Annual Advance
13 | IMDG (Cache Software) - with supporting components for Production environment -Annual Subscription Cost for first year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 113 | M1 - 1 | Annual Advance
14 | IMDG (Cache Software) - with supporting components for Production environment -Annual Subscription Cost for second year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 114 | M1 - 2 | Annual Advance
15 | IMDG (Cache Software) - with supporting components for Production environment -Annual Subscription Cost for third year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 115 | M1 - 3 | Annual Advance
16 | IMDG (Cache Software) - with supporting components for Staging environment - Annual Subscription Cost for first year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 116 | M1 - 1 | Annual Advance
17 | IMDG (Cache Software) - with supporting components for Staging environment - Annual Subscription Cost for second year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 117 | M1 - 2 | Annual Advance
18 | IMDG (Cache Software) - with supporting components for Staging environment - Annual Subscription Cost for third year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 118 | M1 - 3 | Annual Advance
19 | IMDG (Cache Software) - with supporting components for T & D environment - Annual Subscription Cost for first year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 119 | M1 - 1 | Annual Advance
20 | IMDG (Cache Software) - with supporting components for T & D environment - Annual Subscription Cost for second year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 120 | M1 - 2 | Annual Advance
21 | IMDG (Cache Software) - with supporting components for T & D environment - Annual Subscription Cost for third year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 121 | M1 - 3 | Annual Advance
B - Data layer for DR DC-Mandatory
22 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Annual Subscription Cost for first year - for DR DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 201 | M1 - 1 | Annual Advance
23 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Annual Subscription Cost for second year - for DR DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 202 | M1 - 2 | Annual Advance
24 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Annual Subscription Cost for third year - for DR DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 203 | M1 - 3 | Annual Advance
25 | Transactional Data Store -with supporting components for Staging environment - Annual Subscription Cost for first year - for DR DC Note:-If the bidder does not required Subscription for Staging for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 204 | M1 - 1 | Annual Advance
26 | Transactional Data Store -with supporting components for Staging environment - Annual Subscription Cost for second year - for DR DC Note:-If the bidder does not required Subscription for Staging for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 205 | M1 - 2 | Annual Advance
27 | Transactional Data Store -with supporting components for Staging environment - Annual Subscription Cost for third year - for DR DC Note:-If the bidder does not required Subscription for Staging for solution then fill cost as Rs. 1. | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 206 | M1 - 3 | Annual Advance
28 | RDBMS - with supporting components - Annual Subscription Cost for first year - for DR DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 207 | M1 - 1 | Annual Advance
29 | RDBMS - with supporting components - Annual Subscription Cost for second year - for DR DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 208 | M1 - 2 | Annual Advance
30 | RDBMS - with supporting components - Annual Subscription Cost for third year - for DR DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 209 | M1 - 3 | Annual Advance
31 | IMDG (Cache Software) - with supporting components for Production environment -Annual Subscription Cost for first year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 210 | M1 - 1 | Annual Advance
32 | IMDG (Cache Software) - with supporting components for Production environment -Annual Subscription Cost for second year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 211 | M1 - 2 | Annual Advance
33 | IMDG (Cache Software) - with supporting components for Production environment-Annual Subscription Cost for third year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 212 | M1 - 3 | Annual Advance
34 | IMDG (Cache Software) - with supporting components for Staging environment - Annual Subscription Cost for first year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 213 | M1 - 1 | Annual Advance
35 | IMDG (Cache Software) - with supporting components for Staging environment - Annual Subscription Cost for second year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 214 | M1 - 2 | Annual Advance
36 | IMDG (Cache Software) - with supporting components for Staging environment - AnnualSubscription Cost for third year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 215 | M1 - 3 | Annual Advance
C -Installation, Support and Services -Mandatory
37 | Installation and commissioning Charges of supplied products at primary and DR DC | --- | Lumpsum | 1 | Clause 4.1-4.8 | Services (Bidder + OEM) |  | 301 | M1 - 1 | Post Golive
38 | Training Charges | --- | --- | --- | Clause 4.13 | Services (Bidder + OEM) |  | 302 | M2 | On completion
39 | Bidder Charges for Comprehensive support charges for first year | --- | --- | --- | Clause 4.1-4.12 | Services by Bidder |  | 303 | M3 - 1 | Quarterly Deferred
40 | Bidder Charges for Comprehensive support charges for second year | --- | --- | --- | Clause 4.1-4.12 | Services by Bidder |  | 304 | M3 - 2 | Quarterly Deferred
41 | Bidder Charges for Comprehensive support charges for third year | --- | --- | --- | Clause 4.1-4.12 | Services by Bidder |  | 305 | M3 - 3 | Quarterly Deferred
42 | OEM Man days charges for First year for Transactional Data Store | --- | Man days | 35 | Clause 4.12 | Services - OEM Professional Services |  | 306 | M4 - 1 | Half Year Deferred
43 | OEM Man days charges for Second year for Transactional Data Store | --- | Man days | 20 | Clause 4.12 | Services - OEM Professional Services |  | 307 | M4 - 2 | Half Year Deferred
44 | OEM Man days charges for Third year for Transactional Data Store | --- | Man days | 20 | Clause 4.12 | Services - OEM Professional Services |  | 308 | M4 - 3 | Half Year Deferred
45 | OEM Man days charges for First year for RDBMS | --- | Man days | 15 | Clause 4.12 | Services - OEM Professional Services |  | 309 | M4 - 1 | Half Year Deferred
46 | OEM Man days charges for Second year for RDBMS | --- | Man days | 5 | Clause 4.12 | Services - OEM Professional Services |  | 310 | M4 - 2 | Half Year Deferred
47 | OEM Man days charges for Third year for RDBMS | --- | Man days | 5 | Clause 4.12 | Services - OEM Professional Services |  | 311 | M4 - 3 | Half Year Deferred
48 | OEM Man days charges for First year for IMDG (Cache Software) | --- | Man days | 15 | Clause 4.12 | Services - OEM Professional Services |  | 312 | M4 - 1 | Half Year Deferred
49 | OEM Man days charges for Second year for IMDG (Cache Software) | --- | Man days | 10 | Clause 4.12 | Services - OEM Professional Services |  | 313 | M4 - 2 | Half Year Deferred
50 | OEM Man days charges for Third year for IMDG (Cache Software) | --- | Man days | 10 | Clause 4.12 | Services - OEM Professional Services |  | 314 | M4 - 3 | Half Year Deferred
D - Optional Items for Primary DC
51 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Subscription for 4th year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 401
52 | Transactional Data Store -with supporting components and underlying Operating System for Staging environment - Subscription for 4th year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 402
53 | Transactional Data Store -with supporting components for T & D environment - Subscription for 4th year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 403
54 | RDBMS - with supporting components - Subscription for 4th year - for Primary DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 404
55 | IMDG (Cache Software) - with supporting components for Production environment -Subscription for 4th year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 405
56 | IMDG (Cache Software) - with supporting components for Staging environment - Subscription for 4th year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 406
57 | IMDG (Cache Software) - with supporting components for T & D environment - Subscription for 4th year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 407
58 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Subscription for 5th year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 408
59 | Transactional Data Store -with supporting components and underlying Operating System for Staging environment - Subscription for 5th year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 409
60 | Transactional Data Store -with supporting components for T & D environment - Subscription for 5th year - for Primary DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 410
61 | RDBMS - with supporting components - Subscription for 5th year - for Primary DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 411
62 | IMDG (Cache Software) - with supporting components for Production environment -Subscription for 5th year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 412
63 | IMDG (Cache Software) - with supporting components for Staging environment - Subscription for 5th year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 413
64 | IMDG (Cache Software) - with supporting components for T & D environment - Subscription for 5th year - for Primary DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 414
Optional Items for DR DC
65 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Subscription for 4th year - for DR DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 501
66 | Transactional Data Store -with supporting components for Staging environment - Subscription for 4th year - for DR DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 502
67 | RDBMS - with supporting components - Subscription for 4th year - for DR DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 503
68 | IMDG (Cache Software) - with supporting components for Production environment -Subscription for 4th year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 504
69 | IMDG (Cache Software) - with supporting components for Staging environment - Subscription for 4th year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 505
70 | Transactional Data Store -with supporting components and underlying Operating System for Production environment - Subscription for 5th year - for DR DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 506
71 | Transactional Data Store -with supporting components for Staging environment - Subscription for 5th year - for DR DC | S-1 | Solution | 1 | Clause 3 & 4 | Aerospike Database 8.0 Enterprise Edition + Red Hat Enterprise Linux for Virtual Datacentre, Premium |  | 507
72 | RDBMS - with supporting components - Subscription for 5th year - for DR DC Note:- In case of node- based solution ,bidder should calculate the price of total nodes offered and divide it by 12 to quote its equivalent price per core. | S-2 | No. of Cores | 12 | Clause 3 & 4 | Percona MySQL |  | 508
73 | IMDG (Cache Software) - with supporting components for Production environment -Subscription for 5th year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (200GB Node limit) | Total 13 Nodes , right to use up to 17 Nodes ( Designed for only 1TB Data Size) | 509
74 | IMDG (Cache Software) - with supporting components for Staging environment - Subscription for 5th year - for DR DC | S-3 | Solution | 1 | Clause 3 & 4 | Hazelcast Platform Data Store (100Gb 3 Nodes) |  | 510
Optional OEM Man days for 4th and 5th Year
75 | OEM Man days charges for 4th year for Transactional Data Store | --- | Days | 20 | --- | Services - OEM Professional Services |  | 601
76 | OEM Man days charges for 5th year for Transactional Data Store | --- | Days | 20 | --- | Services - OEM Professional Services |  | 602
77 | OEM Man days charges for 4th year for RDBMS | --- | Days | 5 | --- | Services - OEM Professional Services |  | 603
78 | OEM Man days charges for 5th year for RDBMS | --- | Days | 5 | --- | Services - OEM Professional Services |  | 604
79 | OEM Man days charges for 4th year for IMDG (Cache Software) | --- | Days | 10 | --- | Services - OEM Professional Services |  | 605
80 | OEM Man days charges for 5th year for IMDG (Cache Software) | --- | Days | 10 | --- | Services - OEM Professional Services |  | 606

## BOM
Price Bid Format (Mandatory Components for Evaluation)
Sl. | Scope | Site | Description | UoM | Price Type | Yr 1 |  |  | Yr 2 |  |  | Yr 3
[6 empty] | PL | SOR | Qty | PL | SOR | Qty | PL | SOR | Qty | Remarks
1 | Supply | Primary | Transactional Data Store (Incl. OS) - Production | Solution | Annual Subscription | 101 | 1 | 1 | 102 | 2 | 1 | 103 | 3 | 1
2 | Supply | Primary | Transactional Data Store (Incl. OS) - Staging | Solution | Annual Subscription | 104 | 4 | 1 | 105 | 5 | 1 | 106 | 6 | 1 | If the bidder does not required Subscription for Staging for solution then fill cost as Rs. 1.
3 | Supply | Primary | Transactional Data Store (Incl. OS) - T&D | Solution | Annual Subscription | 107 | 7 | 1 | 108 | 8 | 1 | 109 | 9 | 1 | If the bidder does not required Subscription for T&D for solution then fill cost as Rs. 1.
4 | Supply | Primary | RDBMS | No. of Cores | Annual Subscription | 110 | 10 | 12 | 111 | 11 | 12 | 112 | 12 | 12 | In case of node-based solution ,bidder should calculate the price of total nodes offere d and divide it by 12 to quote its equivalent price per core.
5 | Supply | Primary | IMDG (Cache Software) - Production | Solution | Annual Subscription | 113 | 13 | 1 | 114 | 14 | 1 | 115 | 15 | 1
6 | Supply | Primary | IMDG (Cache Software) - Staging | Solution | Annual Subscription | 116 | 16 | 1 | 117 | 17 | 1 | 118 | 18 | 1
7 | Supply | Primary | IMDG (Cache Software) - T&D | Solution | Annual Subscription | 119 | 19 | 1 | 120 | 20 | 1 | 121 | 21 | 1
8 | Supply | DR | Transactional Data Store (Incl. OS) - Production | Solution | Annual Subscription | 201 | 22 | 1 | 202 | 23 | 1 | 203 | 24 | 1
9 | Supply | DR | Transactional Data Store (Incl. OS) - Staging | Solution | Annual Subscription | 204 | 25 | 1 | 205 | 26 | 1 | 206 | 27 | 1 | If the bidder does not required Subscription for Staging for solution then fill cost as Rs. 1.
10 | Supply | DR | RDBMS | No. of Cores | Annual Subscription | 207 | 28 | 12 | 208 | 29 | 12 | 209 | 30 | 12 | In case of node-based solution ,bidder should calculate the price of total nodes offere d and divide it by 12 to quote its equivalent price per core.
11 | Supply | DR | IMDG (Cache Software) - Production | Solution | Annual Subscription | 210 | 31 | 1 | 211 | 32 | 1 | 212 | 33 | 1
12 | Supply | DR | IMDG (Cache Software) - Staging | Solution | Annual Subscription | 213 | 34 | 1 | 214 | 35 | 1 | 215 | 36 | 1
13 | Services | Primary & DR | Installation (DR + DC) |  | Lump sum | 301 | 37 | 1 | --- |  | --- | --- |  | ---
14 | Services | Primary & DR | Training |  | Lump sum | 302 | 38 | 1 | --- |  | --- | --- |  | ---
15 | Services | Primary & DR | Comprehensive Support |  | Annual | 303 | 39 | 1 | 304 | 40 | 1 | 305 | 41 | 1
16 | Services | Primary & DR | Transactional Data Store - OEM Man Days |  | Lump sum | 306 | 42 | 35 | 307 | 43 | 20 | 308 | 44 | 20
17 | Services | Primary & DR | RDBMS - OEM Man Days |  | Lump sum | 309 | 45 | 5 | 310 | 46 | 5 | 311 | 47 | 5
18 | Services | Primary & DR | IMDG (Cache Software) - OEM Man Days |  | Lump sum | 312 | 48 | 15 | 313 | 49 | 10 | 314 | 50 | 10
Price Bid Format (Optional Components not part of Evaluation)
[6 empty] | Yr 4 |  |  | Yr 5
1 | Supply | Primary | Transactional Data Store (Incl. OS) - Production |  | Annual Subscription | 401 |  | 1 | 408 |  | 1
2 | Supply | Primary | Transactional Data Store (Incl. OS) - Staging |  | Annual Subscription | 402 |  | 1 | 409 |  | 1
3 | Supply | Primary | Transactional Data Store (Incl. OS) - T&D |  | Annual Subscription | 403 |  | 1 | 410 |  | 1
4 | Supply | Primary | RDBMS |  | Annual Subscription | 404 |  | 12 | 411 |  | 12
5 | Supply | Primary | IMDG (Cache Software) - Production |  | Annual Subscription | 405 |  | 1 | 412 |  | 1
6 | Supply | Primary | IMDG (Cache Software) - Staging |  | Annual Subscription | 406 |  | 1 | 413 |  | 1
7 | Supply | Primary | IMDG (Cache Software) - T&D |  | Annual Subscription | 407 |  | 1 | 414 |  | 1
8 | Supply | DR | Transactional Data Store (Incl. OS) - Production |  | Annual Subscription | 501 |  | 1 | 506 |  | 1
9 | Supply | DR | Transactional Data Store (Incl. OS) - Staging |  | Annual Subscription | 502 |  | 1 | 507 |  | 1
10 | Supply | DR | RDBMS |  | Annual Subscription | 503 |  | 12 | 508 |  | 12
11 | Supply | DR | IMDG (Cache Software) - Production |  | Annual Subscription | 504 |  | 1 | 509 |  | 1
12 | Supply | DR | IMDG (Cache Software) - Staging |  | Annual Subscription | 505 |  | 1 | 510 |  | 1
13 | Services | Primary & DR | Transactional Data Store - OEM Man Days |  | Lump sum | 601 |  | 20 | 602 |  | 20
14 | Services | Primary & DR | RDBMS - OEM Man Days |  | Lump sum | 603 |  | 5 | 604 |  | 5
15 | Services | Primary & DR | IMDG (Cache Software) - OEM Man Days |  | Lump sum | 605 |  | 10 | 606 |  | 10

## PQ
Bidder Qualification Criteria
Sl. | Parameter | Qualification Criteria | Credentials to be provided | Proof | Owner
1 | Qualification Criteria: Existence of Bidding Entity: Registration Certificate | The Bidder must be a Private or Public Company or a Proprietorship, Partnership firm, LLP, or Society/ Trust. Based on the nature of entity the bidder to submit the requisite documents. | For Companies: Certificate of Incorporation under the Companies Act For Partnership Firms / Limited Liability Partnership (LLP): Partnership Deed or Certificate of registration under the Indian Partnership Act / LLP Act For Societies / Trust: Certificate of Registration with Registrar of Societies For Proprietorship Firms: Attested certificate from Bank(s) clearly indicating the date on which the Bank account was opened in the name of the Proprietorship firm which establishes the existence of the firm for the required period. (Mandatory) | TTPL Incorporation Certificate | TTPL
2 | Existence of Bidding Entity: GST Certificate | Bidder must have a current / valid GST Certificate. | Please upload GST Certificate. (Mandatory) | TTPL GST | TTPL
3 | Financial Turnover | The Bidder's average annual turnover over the last three Financial Years preceding the Financial Year in which the tender has been published must be a minimum of Rs. 58 Crores. | The bidder shall submit Certificate from a Chartered Accountant for Turnover of the Bidder for the stipulated financial years, as per ‘Annexure 2: Financial Turnover of Bidder’ of Standard Bid Document Part-I. Note: – i. If the balance sheet for the immediately preceding financial year has not yet been audited, the same shall be certified by the CA in the above certificate, and in such a case the Financial Turnover for the fourth preceding year shall be mentioned in the CA certificate, and the same shall be considered for the eligibility criteria. ii. For the purpose of Annual Turnover, only the revenue from operations shall be considered. Other incomes such as interest, dividend etc. are excluded from the annual turnover. iii. Credentials of affiliated companies like Parent / Holding Company, Strategic Business Unit, Group Company, Subsidiary / Associate Company, Sister Company etc. will not be taken into consideration. (Mandatory) | CA Certificate and Financial Statements for last 3 years | TTPL
4 | OEM Undertaking | · The bidder shall be an original equipment manufacturer (OEM) or an authorized representative of the respective OEMs. Whenever an authorized Agent/Representative submit bid on behalf of the OEM, the same agent/representative shall not submit a bid on behalf of another OEM in the same tender for the same item/product. · Bidder should provide Authorization letter for all the products as per make & model offered in the bid in the SoR. | Authorization letter from the OEM specific to this tender as per sample Performa given in Annexure-XXI of RFP. In case OEM bids directly, Self-certification and any other document for being OEM. The authorization should include details of Tender No., Name and address of the OEM and the bidder authorized and details of the products for which the bidder has been authorized. (Mandatory) | OEM MAF | All respective OEMs
5 | Relevant Project/Work Experience | The Bidder should have successfully completed / executed Similar Project / Work in India for last five Financial Years preceding the Financial Year in which the tender has been published, and current financial year (up to and including the date of publishing of this tender), herein after referred to as the specified period, having value as under- a) At least one Purchase order or work order costing not less than Rs. 10 crores. Or b) At least two Purchase order or work order each costing not less than Rs. 6.25 . Or c) At least three Purchase order or work order each costing not less than Rs. 5 crores Similar Work is defined as under: - Software/Hardware/Network equipment/IT Security equipment/telecom equipment/ Services supporting IT equipment/Servies for Network equipment/ Services for IT security software and hardware/AMC/ATS/IT Helpdesk/IT manpower for support of IT equipment and any other software/IT hardware/IT network related service or equipment like training, installation, commissioning. d) Purchase order should have been issued during defined specified period. e) work may have been completed or ongoing, both to be considered. | 1. The Bidder shall submit CA certificate as per ‘Annexure XXIV:, detailing projects that meet the relevant Project Experience criteria. 2. Only those Contracts / Work Orders / Agreements shall be considered towards Project / Work Experience which have been issued by a. Any entity (Department / Organization / Autonomous body / PSU/ Local Body/ Authority etc.) wholly or partially owned by State / Central Government. Or b. A Private sector organization which is listed in the National Stock Exchange (NSE) or Bombay Stock Exchange (BSE) in India <and> has an average annual Turnover of INR 500 Crore (revenue from operations) & above during last three (03) financial years preceding the year of publishing of tender. 3. Only those Contracts / Purchase Orders shall be accepted as Past experience wherein the contracts / purchase orders have been placed on the bidder directly by an entity belonging to one of the above categories. 4. In case the contract / purchase order / work order being presented is a composite contract (i.e. it contains items other than the ones defined in the qualification criteria as similar work), only such line items shall be considered which qualify as per the definition of similar work mentioned in the contract. In such cases the value of such line items shall be indicated by the bidder as a separate attachment to annexure XXIV. If the value of contract / line items qualifying as per the definition of similar work is not mentioned separately in such composite contracts/ line items, such contracts / line items shall not be considered towards fulfilment of project / work experience. 5. Bidder shall submit the document/certificate issued by consignee/purchaser for the quantities supplied/activities/stages completed up to the end date of specified period. Value of successfully executed/commissioned work, up to the end date of specified period under the criteria, shall be considered as per payment terms stipulated in contract/tender for the item falling within the definition of similar work criteria. The bidder shall submit a CA Certificate for the detailed calculation of value as claimed by bidder, accordingly. 6. If the purchaser seeks any clarification related to relevant project / Work experience certificates submitted by the bidder, the bidder shall not be permitted to submit any new Contract / Purchase order/ Work order, whose details are not already provided in the original bid. Any such new Contract / Purchase order/ Work order shall not be considered. (Mandatory) | CA Certificate of Projects awarded directly by Gov. or Listed Ent > 500 Cr | TTPL
5.1 | Relevant Project / Work Experience: Copies of Purchase Orders / Contracts/ Work Orders | The Bidder shall submit Copies of Purchase Order (s) / Contract (s) / Work Order (s) (including all associated documents / Annexures) for all the projects/ works mentioned in the CA certificate. | (Mandatory)
5.2 | Relevant Project / Work Experience: Completion Certificates | The Bidder shall submit copies of Satisfactory Completion Certificate(s)/ Performance Certificate (s) issued by the Purchaser / Consignee for all the projects mentioned in the CA certificate submitted. | (Mandatory)
6 | Non-Blacklisting Declaration by Bidder | The Bidder shall submit a self- declaration of non- blacklisting clause of Standard Bid Document Part-I as per ‘Annexure XXVI : Declaration of Non- Blacklisting by Bidder’. | OEMs have to submit the OEM undertaking regarding Non- Blacklisting on OEM letterhead as per the Annexure XXV of RFP. Additionally, the SIs/Bidders are required to submit the declaration/undertaking as per the Annexure XXVI on minimum INR. 100 stamp paper and duly notarized. (Mandatory) | Declaration on Letter head | TTPL / Respective OEMs
7 | Land Border with India Compliance | The Bidder shall submit a self- declaration of compliance to Land Border clause of Standard Bid Document Part-I as per ‘Annexure 7 : Certificate from Bidder for Compliance to GoI Order for Countries sharing Land Border with India’ of Standard Bid Document Part- I. | (Mandatory) | Undertaking by Bidder | TTPL
8 | Make in India | The Bidder shall submit a self- certification of compliance to Make in India Policy as per ‘Annexure 6: Self Certification by Bidder for Make in India’ of Standard Bid Document Part-I. | (Mandatory) | CA Letter of Class 2 Supplier (20%) | TTPL / Respective OEMs

## TQ
Technical Evaluation Requirements
Sl. | Parameter | Technical Requirements | Documents to be provided | Owner
1 | Solution document | Proposed solution along with deployment Architecture in accordance with the minimum requirement specified in deployment architecture defined in section 3 and related Annexures. | Bidders need to submit the solution document along with deployment architecture and also compliance to CRIS proposed architecture and sizing of Data layer (section 3.2) duly vetted by respective OEMs. Note:- The solution document should clearly present the deployment architecture, including detailed replication mechanisms, a high availability (HA) strategy to ensure zero data loss, backup strategy, comprehensive dashboard and monitoring capabilities, and any other relevant components necessary to fulfil the specified requirements. | HPE
2 | Schedule of Requirements (Non-priced SOR) | Make/Version/Model of the offered products as per format given in Annexure II. | Bidder need to clearly specify the Make/Model and details as per format given in Annexure II, for each Item in Schedule of Requirements and mention details of additional products offered to meet the requirements in the remark column of <non- priced>Schedule of Requirements provided in technical bid. No price element to be mentioned otherwise the bid will be summarily rejected. | Respective OEMs
3 | Technical Compliance | Compliance from OEM for detailed technical specifications of all the Products are given in Annexure IV. | The bidder must submit an item wise compliance for the technical specifications duly vetted by the respective OEMs specific to this tender. The Model and Make/Version of the offered products should be clearly specified in this compliance document. | Respective OEMs
4 | Bill of Material (BoM) | Bill of material (BOM) of offered products. | The bidder must furnish the complete Bill of Material (BoM) of all the products on the letter head of the OEM duly vetted by the respective OEM. | Respective OEMs
5 | Technical Use Case report for YCSB for transactional data store | Proposed Solution should provide YCSB benchmark reports given in Annexure XI along with the product used to implement the solution. | Bidder to submit documents for YCSB benchmark report for workload types (as per format given in Annexure XV) having following information: ● Hardware utilization report based on nmon csv format for workload types. ● Product(s) used to implement the workload types for YCSB benchmark report. ● Compliance Certificate from the OEM(s) on their letterhead as per format given in Annexure XVI, whose product is used to implement the solution for the respective workload types. Refer Annexure XI for YCSB benchmarking Criteria, Workload types CRIS reserves the right to ask for the demonstration of the YCSB benchmark to implement the workload types given in Annexure XI | Respective OEMs
6 | Product Support life cycle | The bidder should submit valid letter from all the OEMs | Documentary evidence such as from all OEM/Vendors whose products are being quoted by the Bidder need to be submitted as per sample format given in Annexure XXI (MAF) | Respective OEMs
7 | Product deployment | The key products offered in the subject tender –Transaction Datastore & its components, RDBMS and In Memory Data Grid (caching) should have at least 02 deployment in India for each product in single project or in independent project in the preceding 3 financial years and current year i.e. during 2022-23, 2023-24,2024-25 and current financial year up to the date of closing of tender | OEM of each of the product need to submit undertaking in this regard which should be duly signed by authorized signatory. The undertaking should give details of the installation such as product installed, customer name and financial year , size of installation of deployment of product as per format given in Annexure-VIII Note: In case, the OEM is unable to share the Customer details due to binding of Non- Disclosure Agreement (NDA) signed with the Customer, the OEM needs to mention the same in the above undertaking and provide all other required information. | Respective OEMs
8 | Quality management System | Bidder should have a valid ISO 9001:2015 Quality Management Certification on the date of closing of the Tender | Valid Certificate of each type from the certifying organization. | TTPL
9 | Bidder or OEM support offices availability | Bidder or OEM should have Customer Support offices in the Delhi / NCR region and Secunderabad. In case bidder does not have offices in these places , The bidder may give an undertaking to have offices in these places in case the tender is awarded. The office should be opened within four weeks from the date of awarding of the Tender. | Documents giving complete detail of customer support office. The details of customer support office should include details such as postal address / telephone no., contact nos., qualification & skill set of the engineer/s in the support office as per format given in Annexure 15 of SBD-1. | TTPL / Respective OEMs / HPE
10 | Technical Resource Capability | Bidder to ensure availability of OEM Certified Man-power if the contract is awarded. | Declaration from bidder or details of certified Engineers along with supporting documents clearly giving the certification details, if engineers are available. | TTPL / Respective OEMs / HPE
11 | Declaration of inclusion of OEM Services | The bidder should submit a letter on their letterhead stating required OEM services have been considered as per the terms & conditions of this RFP | The bidder should submit a letter as per Annexure-XVII specific to this tender. | TTPL
12 | Functional Requirement | Compliance from Bidder for detailed functional requirement of all the Products given in Annexure III. | The bidder must submit an item wise compliance for the functional requirement. | TTPL / HPE

## Doc Track
Document Checklist and Tracker
Sl. | Doc Ref. | Doc Description | Owner | Inputs Req. From | Status | Est. Close date | Remarks
1 | Annex - 1A | Details of physical servers for PRS | TTPL | NA | Done
2 | Annex - 1B | List of Software and Hardware components | TTPL | NA | Done
3 | Annex - 1C | Details of DR Data replication | TTPL | NA | Done
4 | Annex - 1D | Backup details | TTPL | NA | Done
5 | Annex - 1E | Detailed Deployment Architecture | TTPL | NA | Done
6 | Annex - 3 | Functional requirements | TTPL | NA | Done
7 | Annex - 9 | FAT Procedure | TTPL | NA | Done
8 | Annex - 10 | Test Certificates - Preliminary Test cert, FAT cert and System commissioning cert | TTPL | NA | Done
9 | Annex - 11 | Technical use cases | TTPL | NA | Done
10 | Annex - 19 | Existing Infra and Tools already at CRIS | TTPL | NA | Done
11 | Annex - 20 | Details of Min OEM Man days for I&C at DC and DR | TTPL | NA | Done
12 | Annex - 5 | Checklist of docs for Qualification Criteria | TTPL
13 | Annex - 7 | Support Office details in Delhi/NCR and Secunderabad | TTPL | TTPL Mgmt. |  |  | Office address for Secunderabad
14 | Annex - 12 | Bidder declaration for Land Border (Annex 7 of GCC) | TTPL | NA
15 | Annex - 13 | NDA | TTPL | NA |  |  | Format
16 | Annex - 17 | Bidder declaration for inclusion of OEM Services | TTPL | OEM BOM
17 | Annex - 24 | Past performance details of bidder | TTPL | CA or Auditor
18 | Annex - 26 | Declaration of Non-Black Listing by Bidder | TTPL | NA
19 | Annex - 2 | Schedule of requirement (SOR) | TTPL | HPE / All OEMs
20 | Annex - 14 | Software component - breakup detail format | TTPL | HPE / All OEMs
21 | Annex - 15 | Bidder format to submit solution for each technical use case | TTPL | HPE / All OEMs
22 | Annex - 22 | Self certificate by Bidder for Make in India (Annex 6 of GCC) | TTPL | All OEMs
23 | Annex - 4 | Technical Specifications Compliance | All OEMs | NA
24 | Annex - 6 | Check list of Docs for Technical Evaluation | All OEMs | NA |  |  | Doc check list
25 | Annex - 8 | OEM product deployment undertaking | All OEMs | NA
26 | Annex - 16 | OEM compliance certificate for Technical use cases solution | All OEMs | NA
27 | Annex - 21 | OEM MAF - OEM Authorization to Bidder and Backend Support Undertaking | All OEMs | NA
28 | Annex - 23 | Installation and Config - Breakup format | All OEMs | HPE / All OEMs
29 | Annex - 25 | Declaration of Non Black Listing by OEM | All OEMs | NA
| Annex G | OEM undertaking
Post Bid - Delivery Documentation Checklist
Sl. |  | Doc Description | Owner | Inputs Req. From | Status | Est. Close date
1 |  | Requirements document as per Design Workshop conducted by Bidder and OEM. | TTPL | HPE / All OEMs
2 |  | High Level Design Document. | TTPL | HPE / All OEMs
3 |  | Low level Design document including Deployment Architecture document with diagram as well as descriptions for both the Primary and DR DC. | TTPL | HPE / All OEMs
4 |  | Implementation Plan | TTPL | HPE / All OEMs
5 |  | Testing Plan and Test Cases | TTPL | HPE / All OEMs
6 |  | Traceability Matrix | TTPL | HPE / All OEMs
7 |  | Installation Reports | TTPL | HPE / All OEMs
8 |  | Documentation of complete setup including installation, configuration, customization, Administration, Maintenance. | TTPL | HPE / All OEMs
9 |  | Product Manuals. | TTPL | HPE / All OEMs
10 |  | Training Materials. | TTPL | HPE / All OEMs
11 |  | Document of Knowledge Transfer (KT) | TTPL | HPE / All OEMs
12 |  | Document of Design Best practices and P&T | TTPL | HPE / All OEMs
13 |  | Any other relevant document | TTPL | HPE / All OEMs

## Del. Sch.
Project Delivery Schedule
Sl. | Task Description Schedule | Weeks from date of issue of Purchase Order (D) for completion | Milestone | Dependency on other milestones | Related item S No. of SoR (Annexure – II)
T1 | Supply of all Software components as specified in SoR for primary and DR site | D + 4 |  | NIL | Item no. 1 to 36
T2 | Installation, configuration of all supplied items at primary and DR site and setting up of Replication along with preparation of installation report along with application migration w.r.t supplied Transaction Data Store | D + 8 |  | T1 | Item no. 37
T3 | Final Acceptance Test Procedure at primary and DR site deployment. | D + 10 |  | T2 | Item no. 37
T4 | System go-live at primary and DR site | D + 14 |  | T3 | Item no. 37
T5 | Commissioning of the system at primary and DR site after 28 days of successful operations. | D + 14 | M1 | T3 | Item no. 1 to 37
T6 | OEM Training | D + 14 | M2 | NIL | Item no. 38
T7 | Commencement of comprehensive maintenance services at Primary and DR Site for 3 years | D + 14 | M3 | T5(M1) | Item no. 39 to 41
T8 | Commencement of OEM man-day support at Primary Site and DR Site for 3 years | D + 14 | M4 | T5(M1) | Item no. 42 to 50

## LD - Penalty
LD / Penalty
Sl. | Task Description Schedule | Weeks from date of issue of Purchase Order (D) for completion | Milestone | Related item S No. of SoR (Annexure – II) | LD (In case of delay in delivery / execution)
T1 | Supply of all Software components as specified in SoR for primary and DR site | D + 4 |  | Item no. 1 to 36 | NIL
T2 | Installation, configuration of all supplied items at primary and DR site and setting up of Replication along with preparation of installation report along with application migration w.r.t supplied Transaction Data Store | D + 8 |  | Item no. 37 | NIL
T3 | Final Acceptance Test Procedure at primary and DR site deployment. | D + 10 |  | Item no. 37 | NIL
T4 | System go-live at primary and DR site | D + 14 |  | Item no. 37 | NIL
T5 | Commissioning of the system at primary and DR site after 28 days of successful operations. | D + 14 | M1 | Item no. 1, 4, 7, 10, 13, 16, 19, 22, 25, 28, 31, 34 and 37 | @ 0.5% of the total value of related SoR items in column (5) for each week or part thereof for each data center. The total LD shall not exceed 10% of the total value of related SoR items in column (5) for each data center
T6 | OEM Training | D + 14 | M2 | Item no. 38 | NIL
T7 | Commencement of comprehensive maintenance services at Primary and DR Site for 3 years | D + 14 | M3 | Item no. 39 to 41 | NIL
T8 | Commencement of OEM man-day support at Primary Site and DR Site for 3 years | D + 14 | M4 | Item no. 42 to 50 | NIL

## SLA - Penalty
Service SLAs and Penalty
Type of Failure | Minimum uptime Required | Max Permissible number of failures per month |  | Max Permissible downtime without penalty per month | Penalty Charge
Total Service failure | 99.9% | 2 |  | Total 0.72 hours (43.2 minutes) together for all components which may disrupt overall services | Rs 5,00,000/- per hour or part thereof of downtime exceeding the defined SLA
SLA | Severity Level | Production Support (Time from call logging with OEM)
Initial Response Service Level Objective | Severity-1 | 30 minutes | A problem that severely impacts use of the software in a production environment (such as loss of production data or in which production systems are not functioning). The situation halts business operations and no procedural work around exists. | 1. Rs. 150,000 per hour (or part thereof) after 30 minutes from the time the same is advised to the Contractor by the Helpdesk/CRIS/IR to the designated e-mail advised by the Contractor for the purpose. 2. If persistence above exceeds two hour from the time the same is advised to the Contractor by the Helpdesk/CRIS/IR to the designated email advised by the Contractor for the purpose, then penalty beyond first two hour of failure will be Rs. 2,50,000/- per hour or part thereof.
| Severity-2 | 30 minutes | A problem where the software is functioning but use in a production environment is severely reduced. The situation is causing a high impact to portions of business operations and no procedural workaround exists. | 1. Rs. 150,000 per hour (or part thereof) after 30 minutes from the time the same is advised to the Contractor by the Helpdesk/CRIS/IR to the designated e-mail advised by the Contractor for the purpose. 2. If persistence above exceeds two hour from the time the same is advised to the Contractor by the Helpdesk/CRIS/IR to the designated email advised by the Contractor for the purpose, then penalty beyond first two hour of failure will be Rs. 2,50,000/- per hour or part thereof.
| Severity-3 | 4 hours | A problem that involves partial, non-critical loss of use of the software in a production environment or development environment. For production environments, there is a medium-to-low impact on business, but business continues to function, including by using a procedural workaround. For development environments, where the situation is causing project to no longer continue or migrate into production. | 1. Rs. 10,000 per hour (or part thereof) after four hours from the time the same is advised to the Contractor by the Helpdesk/CRIS/IR to the designated e-mail advised by the Contractor for the purpose; 2. If persistence above exceeds eight hours from the time the same is advised to the Contractor by the Helpdesk/CRIS/IR to the designated e-mail advised by the Contractor for the purpose, then penalty beyond eight hours of failure will be Rs. 30,000/- per hour or part thereof
| Severity-4 | 1 day | A general usage question, reporting of a documentation error, or recommendation for a future product enhancement or modification. For production environments, there is low-to-no impact on business or the performance or functionality of system. For development environments, there is a medium-to-low impact on business, but business continues to function, including by using a procedural workaround. | Rs. 5,000 per day (or part thereof) after 24 hours from the time the same is advised to the Contractor by the Helpdesk/CRIS/IR to the designated e-mail advised by the Contractor for the purpose.
Non provision or non-performance as per SLA in section 4.12.2 of OEM manpower |  |  |  | Double the average per day remuneration as quoted by the bidder will be imposed as penalty for non-availability of manpower.
Non adherence to the RTO/RPO mentioned in section 4.8.1 |  |  |  | Rs 2,00,000/- per hour or part thereof of downtime exceeding the defined SLA
Measurement | Measurement Interval | Target |  | Penalty
Submission of Monthly Reports | Month | All Reports for the previous month shall be submitted by the 7th of the next month |  | No Penalty
|  | Delay beyond the date of submission |  | Rs.1000 for every day’s delay on an incremental basis.
Manpower Absence of resource | Month | If equivalent skilled resource is provided, then no penalty will apply. Otherwise it would be treated as absence of resource and penalty will be applicable. |  | Absence of resource /Manpower deployed will attract a per month per shift penalty as below: For 0-2 Shift per month - Rs9,000 For >2 to 5 Shift - Rs18,000 For >5 Shift - Rs27,000
The Bidder must ensure the Man-power continuity. In case a resource leaves before completing six months, Penalty of Rs.10,000/- per such instance will be levied.
Critical (9<=CVSS<=10) | High (7<=CVSS<9) | Medium & Low (CVSS<7) | Compliance | Penalty | Criteria
Within 30 Days of Release of Security Patches | Within 45 Days of Release of Security Patches | Within 60 Days of Release of Security Patches | 100% | For Critical severity patches penalty will be Rs 3,000/- per missing security patch | Systems will be scanned on weekly basis by bidder for identifying missing security patches by Nessus or using other Vulnerability Assessment Solution which shall be provided by CRIS
For High severity patches, penalty will be Rs. 1,000/- per missing security patch.

## Payment
Payment Schedule
Sl. | Payment Stage | Project Implementation Milestone |  | Payments as % of total value
1 | System Commissioning at Primary Site and DR Site | M1 | Successful System Commissioning at primary and DR Site Following documents are required to be furnished for primary and DR Site: - 1. Successful completion of Preliminary Testing certificate (Annexure –X section 31.1). 2. Final Acceptance Certificate (Annexure –X section 31.2). 3. System Commissioning Certificate (Annexure –X section 31.3). 4. Consumption of OEM Man-days, if any (attendance sheet duly verified by CRIS). 5. Confirmation of the validity of PBG as per SBD-1 | Payment will be made annually for first year, second year and third year of the cost of ICT Components (Software and Hardware) supplied at primary Site and DR Site (As per SoR, S No. 01 to 36). Payment of first year (As per SOR, S. No. 01, 04, 07, 10, 13, 16, 19, 22, 25, 28, 31 and 34), second year (As per SOR, S. No. 02, 05, 08, 11, 14, 17, 20, 23, 26, 29, 32 and 35),_and third year (As per SOR, S. No. 03, 06, 09, 12, 15, 18, 21, 24, 27, 30, 33 and 36) will be done from commencement of first, second and third year respectively from system commissioning date 100 % of the Implementation cost (As per SoR, S. No. 37).
2 | Training Cost | M2 | 100% cost of Training shall be paid after completion of training to the satisfactions of the consignee and upon furnishing the following documents: - 1. Training Completion certificate from CRIS team (Training should be initiated in parallel to implementation) 2. Confirmation of the validity of PBG as per SBD-1 | 100% of the training cost (As per SoR, S. No. 38)
3 | Comprehensive maintenance support for 03 years | M3 | Payments for comprehensive maintenance support cost will be made every quarter at the end of the quarter on submission of certificate of satisfactory maintenance Confirmation of the validity of PBG as per SBD-1 | Payment will be calculated after deducting penalties if any. Payment will be made on quarterly basis on completion of Help desk support subject to submission of performance certificate (As per SoR, S No.39 to 41).
4 | OEM Man-days for First year, Second year and third year | M4 | On OEM man-day consumption basis to be paid half yearly on submission of OEM man- days consumption certificate. Confirmation of the validity of PBG as per SBD-1 | On submission of documentary proof for OEM Man-days consumption on half yearly basis (As per SoR, S No. 42 to 50) from solution provider.

## RE
Deployment Location | Delhi (Primary site) | Secunderabad (DR Site)
Working Hours | 24 hours (3 shifts of 8 hours each) | 8 hours general shift 9 am to 5 pm
Working Days | All days including holidays and weekends (365 days) | Monday to Friday
Duration | 3 years | 3 years
Count of Engineer per shift | 1 | 1
Skill Level | L1 | L1
Min. Qualification | Engineer (BE/ B. Tech. Or equivalent) | Engineer (BE/ B. Tech. Or equivalent)
Min. Experience | Minimum 2 years of relevant experience in managing RHEL and databases, RDBMS and Transaction data Store. Certified in Transaction data Store | Minimum 2 years of relevant experience in managing Transaction data Store. Certified in Transaction data Store

## RACI
Responsibility Matrix
Sl. | Activity to be performed | CRIS | SI | OEM
1 | Signing of the Contract | R,A | R,A | R,I
2 | Supply of all Software components as specified in SoR for primary and DR site | C,I | R,A | R,A
3 | Submission of Project plan | C | R,A | R,C
4 | Submission of the High-level Design document and deployment architecture for all the supplied components and have it reviewed and approved by the OEMs in consultation with all the stakeholders | C,I | R,A | R,C
5 | Submission of Functional Requirement specification, Software Requirement specification, HLD, and LLD, as per the bid document Scope of work for all Software components of PRS Data layer. | C,I | R,A | R,C
6 | Traceability matrix for verification based on the requirements in the Design Workshop, Scope of Work and Deliverables. | C,I | R,A | R,C
7 | Software installation , configuration and Integration by OEM technical resources as per the approved project plan. | C,I | R,A | R,A
8 | Provisioning of Monitoring Dashboard for all the software components as per the bid document | C,I | R,A | R,A
9 | Provisioning , management and administration for all security services as per the bid document | C,I | R,A | R,A
10 | Integration of PRS data layer software components with CRIS existing systems and applications & other applications in Indian Railways | C,I | R,A | R,A
11 | Provisioning and Management of Backup services as per the bid document. | C,I | R,A | R,A
12 | Configuration of DR replication and required processes for all supplied software components of PRS Data Layer | C,I | R,A | R,A
13 | Final Acceptance Test Procedure at primary and DR site deployment. | R,C | R,A | R,A
14 | System go-live at primary and DR site | R,C | R,A | R,A
15 | Commissioning of the system at primary and DR site after 28 days of successful operations. | R,C | R,A | R,A
16 | Technical training sessions of all software components for PRS Data layer to CRIS Tech Team. | C,I | R,A | R,A
17 | Commencement of comprehensive maintenance services including Resident Engineers (REs) at Primary and DR Site for 3 years | C,I | R,A | R,A
18 | Commencement of OEM man-day support at Primary Site and DR Site for 3 years | C,I | R,A | R,A